## Sheet1
Week Number | Week Commencing | Work To Be Done | Deliverable
Week 0 | 2016-09-19 | Python Programming
Week 1 | 2016-09-26 | Python Programming
Week 2 | 2016-10-03 | Draft 1 of ToR | Draft 1 of ToR
Week 3 | 2016-10-10 | Draft 2 of ToR | Completed ToR
Week 4 | 2016-10-17 | Ethics form | Ethics form
Week 5 | 2016-10-24 | Literature Review (LR) | Draft 1 of LR
Week 6 | 2016-10-31 | Second Draft of LR | Completed LR
Week 7 | 2016-11-07 | Probability Theory Research | Minimum Length of PassSentence Confirmation
Week 8 | 2016-11-14 | Probability Theory Research | Quantity of compromised passwords needed to crack PassSentence Determined
Week 9 | 2016-11-21 | Algorithm design | First algoritm attempt
Week 10 | 2016-11-28 | Algorithm design | Final Algorithm designed
Week 11 | 2016-12-05 | Product Design | Product Design
Week 12 | 2016-12-12 | Prototype Construction | Prototype
Week 13 | 2017-01-09 | JavaScript Programming | First draft of JavaScript
Week 14 | 2017-01-16 | Evaluation Design (ED) | Secong Draft of JavaScript
Week 15 | 2017-01-23 | ED/ JavaScript | First Draft of ED
Week 16 | 2017-01-30 | ED Draft 2 | Complete ED
Week 17 | 2017-02-06 | Product Construction | Final Product
Week 18 | 2017-02-13 | Report Outline (RO) | First draft of RO
Week 19 | 2017-02-20 | RO Draft 2 | Complete RO
Week 20 | 2017-02-27 | Presentation Slides | Presentation Slides Draft 1
Week 21 | 2017-03-06 | Presentation Practise | Presentation Slides Draft 2
Week 22 | 2017-03-13 | Presentation Practise | Practise Presentation
Week 23 | 2017-03-20 | Presentation Practise | Practise Presentation
Week 24 | 2017-03-27 | Presentation Practise | Practise Presentation
Week 25 | 2017-04-24 | Prepare Report, Product and Presentation slides for submission | Complete Presentation and submit all final items of competed project